## TESTCASES
Project : WAPL
Module : WAPL Application
URL : https://wynara-pg-test-244339282533.us-central1.run.app/
Test Scenario Description | Test Case ID | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Prority
Verify URL | TC_WAPL_01 | Verify User is in Valid URL | Verify user can Check URL is Valid | 1. Open browser 2. Enter URL | URL : https://wynara-pg-test-244339282533.us-central1.run.app/ | Home page should display | User is in home page | Pass | Hign
Click GET YOUR WAPL ID | TC_WAPL_02 | Verify user can click on GET YOUR WAPL ID | User in Home page | 1. Enter URL 2.Click on GET YOUR WAPL ID |  | Registration page should open | User can go to Registration page | Pass | Hign
Create Account Page | TC_WAPL_03 | Verify Create Account page displayed | Verify user can Check the Create Account | 1. Enter URL 2.Click on GET YOUR WAPL ID 3. User is in Create Account page |  | Create Account page displayed | User is in Create Account page | Pass | Hign
Enter Full Name | TC_WAPL_04 | Verify user can enter Valid name in Full Name Text Box | User in Register page | 1. User is in Registration page 2. Enter Full Name | Full Name : Macha Venkatesh | Name should accept | Name should accept | Pass | Hign
Enter Email | TC_WAPL_05 | Verify user can enter Valid name in Email Text Box | Enter the Valid Email | 1. User is in Registration page 2. Enter Email | Email : machavenkatesh869@gmail.com | Email accepted | User Entered Email | Pass | Hign
Enter Phone Number | TC_WAPL_06 | Verify user can enter Valid name in Phone number Text Box | Enter the Valid Phone Number | 1. User is in Registration page 2. Phone Number | Ph : 8639082431 | Phone accepted | User Entered PH | Pass | Hign
Enter Address | TC_WAPL_07 | Verify user can enter Valid name in Address Text Box | Enter the Valid Address | 1. User is in Registration page 2. Enter Address | Address : Hanuman Nagar , Proddatur | Address accepted | User Entered Address | Pass | Medium
Click DevOps Checkbox | TC_WAPL_08 | Verify user can Click DevOps Check Box | User Click on Checkbox | 1. User is in Registration page 2. Click on Checkbox | Clicked | Checkbox selected | User Clicked on DevOps | Pass | Hign
Enter Password | TC_WAPL_09 | Verify user can enter Valid name in Password Text Box | Enter the Valid Password | 1. User is in Registration page 2. Enter Password | Pass : 123456 | Password accepted | User Entered Pass | Pass | Hign
Enter Confirm Password | TC_WAPL_10 | Verify user can enter Valid name in Confirm Password Text Box | Enter the Valid Confirm Password | 1. User is in Registration page 2. Enter Same Password | Confirm Pass : 123456 | Password match accepted | User Entered Confirm Pass | Pass | Hign
Click Register | TC_WAPL_11 | Verify user can click on register Button | All fields filled | 1. User is in Registration page 2. Click on Register Button | Clicked | A Pop Msg Like " Register Success" and navigated to OTP Page | Success message and OTP page | Pass | Hign
Enter OTP | TC_WAPL_12 | Verify OTP functionality | OTP page open | 1. User is in OTP Page 2. Enter OTP 3. Click on Verify Identity | OTP from email | Registration complete | Registration complete | Pass | Hign
Click Login | TC_WAPL_13 | Verify User can click on Member Login | User is in Home Page | 1. Enter URL 2.Click on Member Login |  | Login Page Should be Open | User Should be navigated to login page | Pass | High
Verify Login | TC_WAPL_14 | Verify Login with Valid Credentials | User is in Login page | 1. Enter Valid Email 2.Valid Password 3. Click on Sign In | Email : sandygadypreethi@gmail.com Pass : 123456 | Login Success | User Logged In | Pass | High
Verify Login | TC_WAPL_15 | Verify Login with Invalid Credentials | User is in Login page | 1. Enter Invalid Email 2.Valid Password 3. Click on Sign In | Email : xxx@gmail.com Pass : 123457 | A Pop msg Like "Invalid email or password" | Login Fail | Fail | High
Verify Login | TC_WAPL_16 | Verify Login with Invalid Credentials | User is in Login page | 1. Enter Valid Email 2.Invalid Password 3. Click on Sign In | Email : sandygadypreethi@gmail.com Pass : 111111 | A Pop msg Like "Invalid email or password" | Login Fail | Fail | High
Verify Login | TC_WAPL_17 | Verify Login with Invalid Data | User is in Login page | 1. Enter Invalid Email 2.Invalid Password 3. Click on Sign In | Email : xxxx@gmail.com Pass : 111111 | A Pop msg Like "Invalid email or password" | Login Fail | Fail | High
Verify Login | TC_WAPL_18 | Verify Login with Blank Data | User is in Login page | 1. Without Email 2.Without Password 3. Click on Sign In | Email : Pass : | A Pop msg Like "Please Fill Fields" | Login Fail | Fail | High
Verifying the Registration Functionality | TC_WAPL_19 | User can fill all the required details in the registration page without selecting the domain | User is in Registration Page | 1. Enter URL 2.Click on GET YOUR WAPL ID 3. User is in Create Account page | Full Name : Macha Venkatesh Email : sandygadupreethi@gmail.com Ph : 8639082431 Add : 4/1321, HANUMAN NAGAR, PRODDATUR Pass : 123456 Con Pass : 123456 | A Msg Should be Displayed as "Please select at least one domain" | A Msg Should be Displayed as "Please select at least one domain" | Fail | High
Verifying the Registration Functionality | TC_WAPL_20 | User can fill all the required details in the registration page without Filling the Phone Number | User is in Registration Page | 1. Enter URL 2.Click on GET YOUR WAPL ID 3. User is in Create Account page | Full Name : Macha Venkatesh Email : sandygadupreethi@gmail.com Ph : Add : 4/1321, HANUMAN NAGAR, PRODDATUR Domain : DevOps Pass : 123456 Con Pass : 123456 | A Pop Msg Should be Displayed as "Please Fill in the Field" | A Pop Msg is Displayed | Fail | High
Verifying the Registration Functionality | TC_WAPL_21 | User can fill all the required details in the registration page without Filling the E-Mail | User is in Registration Page | 1. Enter URL 2.Click on GET YOUR WAPL ID 3. User is in Create Account page | Full Name : Macha Venkatesh Email : Ph : 8639082431 Add : 4/1321, HANUMAN NAGAR, PRODDATUR Domain : DevOps Pass : 123456 Con Pass : 123456 | A Pop Msg Should be Displayed as "Please Fill in the Field" | A Pop Msg is Displayed | Fail | High
Verifying the Registration Functionality | TC_WAPL_22 | User can fill all the required details in the registration page without Filling the E-Mail | User is in Registration Page | 1. Enter URL 2.Click on GET YOUR WAPL ID 3. User is in Create Account page | Full Name : Macha Venkatesh Email : Ph : 8639082431 Add : 4/1321, HANUMAN NAGAR, PRODDATUR Domain : DevOps Pass : 123456 Con Pass : 123456 | A Pop Msg Should be Displayed as "Please Fill in the Field" | A Pop Msg is Displayed | Fail | High
Verifying the Registration Functionality | TC_WAPL_23 | User can fill all the required details in the registration page without Filling the Password | User is in Registration Page | 1. Enter URL 2.Click on GET YOUR WAPL ID 3. User is in Create Account page | Full Name : Macha Venkatesh Email : Ph : 8639082431 Add : 4/1321, HANUMAN NAGAR, PRODDATUR Domain : DevOps Pass : Con Pass : 123456 | A Pop Msg Should be Displayed as "Please Fill in the Field" | A Pop Msg is Displayed | Fail | High
Verifying the Registration Functionality | TC_WAPL_24 | User can fill all the required details in the registration page without Filling the Confirm Password | User is in Registration Page | 1. Enter URL 2.Click on GET YOUR WAPL ID 3. User is in Create Account page | Full Name : Macha Venkatesh Email : Ph : 8639082431 Add : 4/1321, HANUMAN NAGAR, PRODDATUR Domain : DevOps Pass : 123456 Con Pass : | A Pop Msg Should be Displayed as "Please Fill in the Field" | A Pop Msg is Displayed | Fail | High
Verifying the Registration Functionality | TC_WAPL_25 | User can click on Register without Filling the All Details | User is in Registration Page | 1. Enter URL 2.Click on GET YOUR WAPL ID 3. User is in Create Account page | Full Name : Email : Ph : Add : Domain : Pass : Con Pass : | A Pop Msg Should be Displayed as "Please Fill in the Field" | A Pop Msg is Displayed | Fail | High
Verifying Homepage After Login | TC_WAPL_26 | User can see their WAPL ID After Login With Valid Credentials After the Admin Approval | User is in Home Page | 1. Login With Valid Data 2. After Admin Was Approved 2. User Navigated to Homepage |  | A WAPL ID was Generated After User can Login with Valid Credentials | WAPL ID Generated | Pass | High
Verifying Homepage After Login | TC_WAPL_27 | User can see their Status After Login With Valid Credentials After the Admin Approval | User is in Home Page | 1. Login With Valid Data 2. After Admin Was Approved 2. User Navigated to Homepage |  | A Status was Displayed as "Approved" | Status is Displayed | Pass | High
Verifying Homepage After Login | TC_WAPL_28 | User can see their Domain After Login With Valid Credentials After the Admin Approval | User is in Home Page | 1. Login With Valid Data 2. After Admin Was Approved 2. User Navigated to Homepage |  | A Domain Displayed as which is selected by the user | User Selected Domain is Displayed | Pass | High
Verifying Homepage After Login | TC_WAPL_29 | User can see their PH After Login With Valid Credentials After the Admin Approval | User is in Home Page | 1. Login With Valid Data 2. After Admin Was Approved 2. User Navigated to Homepage |  | Phone Number is displayed the user is submitted in the Registration Form | Phone Number is Displayed | Pass | High
Verifying Homepage After Login | TC_WAPL_30 | User can see their Name at the top of the homepage After Login With Valid Credentials After the Admin Approval | User is in Home Page | 1. Login With Valid Data 2. After Admin Was Approved 2. User Navigated to Homepage |  | The User Name is Displayed | Username Displayed | Pass | High
Verifying Homepage After Login | TC_WAPL_31 | User can see the WAPL logo at the top of the Home Page | Video Logo is Diaplayed | 1. Login With Valid Data 2. After Admin Was Approved 2. User Navigated to Homepage |  | Video logo is Displayed | Video logo displayed | Pass | High
Verifying the Edit Button in Dashboard | TC_WAPL_32 | Verify User can click the Edit the Personal Information Option | User is in Homepage | 1. After Login 2.Click on Edit Option in personal Information in Dashboard |  | User is in personal information page | User navigated to personal information page | Pass | High
Fill the details in Personal Information | TC_WAPL_33 | Verify User can change the details at any time | User is in My Profile Page | 1. After Login 2.Click on Edit Option in personal Information in Dashboard Module 3.User is can edit the details 4.Click on save | F N : Venkatesh Phone : 8639082431 Add : Hanuman Nagar, Proddatur | A Pop Msg like "Profile Saved Successfully! " displayed | Profile Saved Successfully msg was displayed | Pass | High
Fill the details in Personal Information | TC_WAPL_34 | Verify User can upload the resume | User can Upload their Resume | 1.User is in My Profile Page 2. Upload the resume |  | A Link was generated after Upload above the resume | A Link was generated after Upload | Pass | High
Verifying the modules are available in the homepage | TC_WAPL_35 | Verify the Modules Which are Displayed | User see the Modules | 1. Login With Valid Data 2. After Admin Was Approved 3. User Navigated to Homepage click on My Profile |  | The Modules Are : Dashboard , My Profile , Exam , Certificate , Logout | The Modules are Displayed | Pass | High
Verifying the My Profile module | TC_WAPL_36 | User can see the My Profile module are available in the homepage | User is in My Profile Page | 1. Login With Valid Data 2. After Admin Was Approved 3. User Navigated to Homepage click on My Profile |  | User see the Personal Information Detais, Skills and Project | Yes Available | Pass | High
Verifying Profile Pic | TC_WAPL_37 | User can Upload and change the profile pic at any time | User is in My Profile Page | 1. Login With Valid Data 2. After Admin Was Approved 3. User Navigated to Homepage click on My Profile | Profile Pic | User can Upload their Profile Pic | User can Upload their Profile Pic | Pass | High
Verifying Personal Details | TC_WAPL_38 | User can change the personal details at any time | User is in My Profile Page | 1. Login With Valid Data 2. After Admin Was Approved 3. User Navigated to Homepage click on My Profile |  | Personal Details change at any time | Personal Details change at any time | Pass | High
Verifying Exam Module | TC_WAPL_39 | User can click on exam Module | User is in Exam Module | 1. Login With Valid Data 2. After Admin Was Approved 3. User Navigated to Homepage click on Exam |  | User can see the "Available Exam Schedules" | User can see the "Available Exam Schedules" | Pass | High
Verifying Certificate Module | TC_WAPL_40 | User can click on Certificate Module | User is in Certificate Module | 1. Login With Valid Data 2. After Admin Was Approved 3. User Navigated to Homepage click on Certificate |  | User can see the their certificate after the completion of their course | Certificate is generated after the completion os their course | Pass | High
Verifying Logout Module | TC_WAPL_41 | User can click on Logout Module | User is in My Logout | 1. Login With Valid Data 2. After Admin Was Approved 3. User Navigated to Homepage click on Logout |  | User can Logout at any time | User can Logout at any time | Pass | High
Verify Registration Page | TC_WAPL_42 | User can fill the already registered details | User is in registration page | 1. Launch the Application 2.Fill the Fields with already Registered details |  | User the see the msg Like "You already have an active account (WAPL ID: WAPL-2026-DS-0001). Please log in to your existing account instead of creating a new one." | The Msg is Displayed | Pass | High
Verify the URL with different browers | TC_WAPL_43 | Open URL in different Browsers | Verify user can Check URL is running on different browsers | 1. Launch the Application in Chrome 2. Launch the Application in Safari 3. Launch the Application in Edge 4. Launch the Application in Opera | URL : https://wynara-pg-test-244339282533.us-central1.run.app/ | Successfully Running on different browsers | Successfully Running on different browsers | Pass | High

## STUDENT PORTAL DEFECTS
DEFECTS
DEFECTID | DEFECT STATUS | DEFECT DESCRIPTION | STEPS TO REPRODUCE | EXPECTED RESULTS | ACTUAL RESULTS | SEVERITY | PRIORITY | STATUS | SCREENSHOTS | RETEST STATUS | COMMENTS | AFTER RETEST SCREENSHOTS
DEFECT_Myprofile_01 | FIXED | PROFILE PIC IS NOT SHOWING AFTER UPLOADING THE PIC | 1. LAUNCH THE APPLICATION 2. LOGIN WITH VALID CREDENTIALS 3. CLICK ON MY PROFILE | PROFILE PIC IS DISPLAYED | PROFILE PIC IS NOT DISPLAYED | MEDIUM | MEDIUM | FAIL |  | PASS | RETESTED AND WORKING AS EXPECTED
DEFECT_Myprofile_02 | NEW | SAVE OR ADD AND EDIT BUTTON IS NOT SHOWING IN EDUCATION AND PROJECTS AFTER FILLING THE USER DETAILS | 1. LAUNCH THE APPLICATION 2. LOGIN WITH VALID CREDENTIALS 3. CLICK ON MY PROFILE | UPGRADE ADD AND EDIT BUTTON , BECAUSE THE USER FEEL GOOD | ADDED AND EDIT BUTTON IS NOT SHOWING | HIGH | HIGH | FAIL
DEFECT_Registration_03 | NEW | FULL NAME IS ALLOWING DIGITS AND SPECIAL CHARS , IT ALLOWS ONLY ALPHABETS | 1. LAUNCH THE APPLICATION 2. CLICK ON GET YOUR WAPL ID | FULL NAME IS ONLY ACCEPTS ALPHABETS | IT ALLOWING DIGITS AND SPECIAL CHARACTERS | MEDIUM | HIGH | FAIL
DEFECT_Registration_04 | NEW | PHONE NUMBER IS ALLOWING ALPHABETS AND SPECIAL CHARS | 1. LAUNCH THE APPLICATION 2. CLICK ON GET YOUR WAPL ID | PHONE NUMBER ACCEPT ONLY NUMERICS | IT ALLOWING ALPHABETS AND SPECIAL CHARS | MEDIUM | HIGH | FAIL
DEFECT_Registration_05 | NEW | EMAIL IS ACCEPTING WITHOUT .COM | 1. LAUNCH THE APPLICATION 2. CLICK ON GET YOUR WAPL ID | EMAIL SHOULD ACCEPT WITH .COM IS MANDATORY | IT ACCEPTING WITHOUT .COM | HIGH | HIGH | FAIL
DEFECT_Registration_06 | NEW | FULL NAME , EMAIL, PHONE NUMBER , PASSWORD AND CONFIRM PSWRD ARE ALLOWING SPACES IN FRONT OF THE CHARACTERS | 1. LAUNCH THE APPLICATION 2. CLICK ON GET YOUR WAPL ID | STARTING AND ENDING WITHOUT SPACE THE USER CAN ENTER THE DETAILS | IT ACCEPTING THE SPACES INFORNT OF THE NAMES | HIGH | HIGH | FAIL
DEFECT_LOGIN_07 | NEW | IN LOGIN EMAIL IS ACCEPTING .COM AS CAPITAL LETTERS | 1. LAUNCH THE APPLICATION 2. CLICK ON LOGIN | EMAIL SHOULD ACCEPT ONLY SMALL LETTERS | IT ACCEPTING THE SOME SMALL AND SOME CAPS LETTERS | HIGH | HIGH | FAIL
DEFECT_Registration_08 | NEW | IN REGISTRATION PAGE PASSWORD DOSEN'T HAVE EYE ICON TO SEE THE PSWRD | 1. LAUNCH THE APPLICATION 2. CLICK ON GET YOUR WAPL ID | EYE ICON MUST SHOULD HAVE TO SEE THE PSWRD TO CHECK THE USER ONCE | IT ICON IS NOT AVAILABLE | HIGH | HIGH | FAIL
DEFECT_MY PROFILE _09 | NEW | IN MYPROFILE PAGE THE EDUCATION AND PERSONAL INFORMATION FILELDS ARE ACCEPTING THE SPACES FROM STARTING | 1. LAUNCH THE APPLICATION 2. CLICK ON LOGIN 3. ENTER VALID CREDENTIALS 4. CLICK ON MYPROFILE | FILEDS SHOULD START AND END WITH WITHOUT SPACES | FILEDS SHOULD START AND ENDING WITH SPACES | HIGH | HIGH | FAIL
DEFECT_MY PROFILE _10 | NEW | IN EDUCATION , THE YEAR FIELD IS ACCEPTING THE ALPHABETS AND OTHER SPL CHARS | 1. LAUNCH THE APPLICATION 2. CLICK ON LOGIN 3. ENTER VALID CREDENTIALS 4. CLICK ON MYPROFILE | YEAR SHOULD ACCEPT ONLY DIGITS | IT ACCEPTING ALPHABETS AND OTHER SPL CHARS | MEDIUM | HIGH | FAIL
DEFECT_MY PROFILE _11 | NEW | SKILLS FIELD IS ACCEPTING NUMERICS IT ONLY ALLOWS ALPHABETS | 1. LAUNCH THE APPLICATION 2. CLICK ON LOGIN 3. ENTER VALID CREDENTIALS 4. CLICK ON MYPROFILE | SKILLS SHOULD ACCEPT ONLY ALPHABETS | IT NUMERICS AND OTHER SPL CHARS | MEDIUM | HIGH | FAIL
DEFECT_MY PROFILE _12 | NEW | AFTER THE ADMIN APPROVAL THE APPROVE NAME HAS SHOWING AT THE TOP IN THE MYPROFILE PAGE IT SHOWING (approveD) | 1. LAUNCH THE APPLICATION 2. CLICK ON LOGIN 3. ENTER VALID CREDENTIALS 4. CLICK ON MYPROFILE | THE STATUS IT STARTS FROM CAPTIAL LETTER | IT SHOWING STARTING SMALL LETTER | LOW | LOW | FAIL
DEFECT_MY PROFILE _13 | NEW | BEFORE UPLOADING THE RESUME THE USER CAN'T SEE WHICH TYPE OF DOCUMENT SHOULD UPLOAD WE WILL ADD THE TEXT LIKE *PDF OR WORD DOCUMENTS ONLY ALLOWED | 1. LAUNCH THE APPLICATION 2. CLICK ON LOGIN 3. ENTER VALID CREDENTIALS 4. CLICK ON MYPROFILE | MENTION THE TEXT LIKE *PDF OR WORD | NO TEXT | MEDIUM | MEDIUM | FAIL
DEFECT_DASHBOARD _14 | NEW | RESUME AND CERTIFICATE BELOW TEXT AS WITH SMALL LETTERS | 1. LAUNCH THE APPLICATION 2. CLICK ON LOGIN 3. ENTER VALID CREDENTIALS 4. CLICK ON DASHBOARD | The status text should be in below the resume "Documents Available" and in Certificate"No Active Certificate" | The status text is displayed in lowercase: "Documents available " and "No active certificate" | LOW | LOW | FAIL
DEFECT_DASHBOARD _15 | NEW | IN REGISTRATION AND LOGIN PAGE THE UPPER TEXT SHOULD NOT DISPLAYED CLEARLY | 1. LAUNCH THE APPLICATION | THE TEXT "VERIFIED. YOURS." SHOULD BE VISIBLE CLEARLY | THE TEXT "VERIFIED " TEXT IS UNDER THE SEARCH BAR | LOW | LOW | FAIL
DEFECT_DASHBOARD _16 | NEW | IN REGISTRATION AND LOGIN PAGE THE BACKGROUND LOGO IS NOT DISPLAYED CLEARLY IT IS CUTTED AT UPPER AND LOWER | 1. LAUNCH THE APPLICATION | THE LOGO IS VISIBLE CLEARLY | THE LOGO IS NOT VISIBLE CLEARLY | LOW | LOW | FAIL
DEFECT_DASHBOARD _17 | NEW | LOGIN IN CERTIFICATE MODULE , AFTER ADMIN ISSUED THE CERTIFICATE THE NAME VISIBLE FOR THE USER , IF IT VISIBLE IT LOOKS GOOD | 1. LAUNCH THE APPLICATION 2. LOGIN WITH VALID CREDENTIALS 3. ADMIN ISSUED THE CERTIFICATE 4. CLICK ON CERTIFICATE | STUDENT NAME IS VISIBLE | STUDENT NAME IS NOT VISIBLE | MEDIUM | MEDIUM | FAIL
DEFECT_DASHBOARD _18 | NEW | ADMIN GIVE ACTIVE STATUS TO THE STUDENT THE STATUS TEXT IS STARTED WITH SMALL LETTER , SO IT STARTS WITH CAPS | 1. LAUNCH THE APPLICATION 2. LOGIN WITH VALID CREDENTIALS 3. CLICK ON DASHBOARD | STATUS TEXT IS "Status" | IT IS VISIBLE LIKE 'status' | LOW | LOW | FAIL

## ADMIN PORTAL
ADMIN PORTAL DEFECTS
DEFECTID | DEFECT STATUS | DEFECT DESCRIPTION | STEPS TO REPRODUCE | EXPECTED RESULTS | ACTUAL RESULTS | SEVERITY | PRIORITY | STATUS | SCREENSHOTS | RETEST STATUS | COMMENTS | AFTER RETEST SCREENSHOTS
DEFECT_ADMIN_01 | FIXED | ADMIN ADDING THE BULK UPLOAD IN STUDENT MODULE IT IS NOT UPLOADING | 1. ADMIN LOGIN 2.CLICK ON STUDENT MODULE 3.CLICK ON BULK UPLOAD 4.Upload a CSV or Excel (.xlsx) file 5. CLIK ON UPLOAD AND CREATE STUDENTS BUTTON | IT UPLOAD THE STUDENT INFORMATION | IT IS NOT UPLOADING IT THROWING A ERROR MSG | HIGH | HIGH | FAIL |  | PASS | RETESTED AND WORKING AS EXPECTED
DEFECT_ADMIN_02 | NEW | ADMIN CLICKING ON THE MODULES IT IS CHANGING FROM UP AND DOWN | 1. ADMIN LOGIN 2.CLICK ON MODULES | NO CHANGES MODULES ARE FIXED | MODULES ARE CHANGING | MEDIUM | HIGH | FAIL
THE ADMIN ADDING THE NEW STUDENT IN STUDENT MODULE WHILE THE ADMIN UPLOADING THE STUDENT PROFILE PIC IN THAT TIME UPLOAD MESSAGE DISPLAYING, AFTER THE ADMIN VIEW IT IS NOT SHOWING | NEW | PROFILE PIC IS NOT DISPLAYING | 1. ADMIN LOGIN 2.CLICK ON STUDENT MODULE 3.CLICK ON NEW STUDENT UPLOAD THE PROFILE PIC | PROFILE PIC IS UPLOADED AND ADMIN CAN VIEW IT | IT IS UPLOADING BUT NOT SHOWING | LOW | LOW | FAIL
THE ADMIN ADDING THE NEW STUDENT IN STUDENT MODULE WHILE THE ADMIN UPLOADING THE STUDENT RESUME IN THAT TIME UPLOAD MESSAGE DISPLAYING, AFTER THE ADMIN VIEW IT IS NOT SHOWING | NEW | RESUME IS NOT DISPLAYING | 1. ADMIN LOGIN 2.CLICK ON STUDENT MODULE 3.CLICK ON NEW STUDENT UPLOAD THE RESUME | RESUME IS UPLOADED AND ADMIN CAN VIEW IT | IT IS UPLOADING BUT NOT SHOWING | LOW | LOW | FAIL
IN ACTIVITY LOGS THE ADMIN AND DO ANY ACTIVITY THE PRESENT TIME IS NOT SHOWING | NEW | WRONG TIME IS SHOWING | 1. ADMIN LOGIN 2.CLICK ON ACTIVITY MODULE 3. AND DO ANY ACTIVITY LIKE DELETE , ADD , UPDATE 4. OBSERVE THE TIME | PRESENT TIME WILL SHOW | IT IS SHOWING WRONG TIME | LOW | LOW | FAIL

## ADMIN TESTCASES
Project : WAPL
Module : WAPL Application
URL : https://wynara-pg-test-244339282533.us-central1.run.app/secure-admin-panel/wapl/login
Test Scenario Description | Test Case ID | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Prority
Verify URL | TC_WAPL-01 | Verify User can click on Member Login | User is in login Page | 1. Enter URL 2.Click on Member Login |  | Login Page Should be Open | User Should be navigated to login page | Pass | High
Verify Login | TC_WAPL_02 | Verify Login with Valid Credentials | User is in Login page | 1. Enter Valid Email 2.Valid Password 3. Click on Sign In | Email : admin@wapl.com Pass : admin@123 | Login Success | User Logged In | Pass | High
Verify Login | TC_WAPL_03 | Verify Login with Invalid Credentials | User is in Login page | 1. Enter Invalid Email 2.Valid Password 3. Click on Sign In | Email : admin@gmail.com Pass : admin@123 | A Pop msg Like "Invalid email or password" | Login Fail | Fail | High
Verify Login | TC_WAPL_04 | Verify Login with Invalid Credentials | User is in Login page | 1. Enter Valid Email 2.Invalid Password 3. Click on Sign In | Email : admin@wapl.com Pass : 111111 | A Pop msg Like "Invalid email or password" | Login Fail | Fail | High
Verify Login | TC_WAPL_05 | Verify Login with Invalid Data | User is in Login page | 1. Enter Invalid Email 2.Invalid Password 3. Click on Sign In | Email : admin@wapl.com Pass : 111111 | A Pop msg Like "Invalid email or password" | Login Fail | Fail | High
Verify Login | TC_WAPL_06 | Verify Login with Blank Data | User is in Login page | 1. Without Email 2.Without Password 3. Click on Login In | Email : Pass : | A Pop msg Like "Please Fill Fields" | Login Fail | Fail | High
Verifying Admin Dashboard | TC_WAPL_07 | Verify that clicking on Dashboard module loads the main dashboard view | User must be logged in as Super Admin. | 1. Log in to the WAPL Admin using valid Super Admin credentials. 2. Navigate to the Dashboard from the sidebar menu. |  | Admin can you the Dashboard | Dashboard Page is Opened | Pass | High
Verifying Admin Dashboard | TC_WAPL_08 | Verify TOTAL STUDENTS Count is Displayed | User must be logged in as Super Admin. | 1. Log in to the WAPL Admin using valid Super Admin credentials. 2. Navigate to the Dashboard from the sidebar menu. 3. Observe the TOTAL STUDENTS count after the student Registration | Add a 3 new students , TOTAL STUDENTS should update to 3. Delete a student , TOTAL STUDENTS should update to 2. No students in the TOTAL STUDENTS should display 0 | The TOTAL STUDENTS box with Count should be visible on the dashboard. | Total Student Count is Displaying | Pass | High
Verifying Admin Dashboard | TC_WAPL_09 | Verify PENDING STUDENTS Count is Displayed | User must be logged in as Super Admin. | 1. Log in to the WAPL Admin using valid Super Admin credentials. 2. Navigate to the Dashboard from the sidebar menu. 3. Observe the PENDING STUDENTS count after the student Registration | Register 1 student, then Admin can Observe the Pending Approval count in Dashboard | The PENDING STUDENTS box with Count should be visible on the dashboard. | Pending Student Count is Displaying | Pass | High
Verifying Admin Dashboard | TC_WAPL_10 | Verify Active Students Count is Displayed | User must be logged in as Super Admin. | 1. Log in to the WAPL Admin using valid Super Admin credentials. 2. Navigate to the Dashboard from the sidebar menu. 3. Observe the Active Students count after the student Registration | Activate 1 student and observe the Active Students count in Dashboard | The Active Students box with Count should be visible on the dashboard. | Active Student Count is Displaying | Pass | High
Verifying Admin Dashboard | TC_WAPL_11 | Verify Suspended Students Count is Displayed | User must be logged in as Super Admin. | 1. Log in to the WAPL Admin using valid Super Admin credentials. 2. Navigate to the Dashboard from the sidebar menu. 3. Observe the Suspended Students count after the student Registration | Suspend 1 student and observe the Suspended Students count in Dashboard | The Suspended Students box with Count should be visible on the dashboard. | Suspended Student Count is Displaying | Pass | High
Verifying Admin Dashboard | TC_WAPL_12 | Verify Total HRs Count is Displayed | User must be logged in as Super Admin. | 1. Log in to the WAPL Admin using valid Super Admin credentials. 2. Navigate to the Dashboard from the sidebar menu. 3. Observe the HRs count after the adding the New HR | Add 1 HR and observe the HRs count in Dashboard | The Hrs box with Count should be visible on the dashboard. | Hrs Count is Displaying | Pass | High
Verifying Admin Dashboard | TC_WAPL_13 | Verify Active Domains Count is Displayed | User must be logged in as Super Admin. | 1. Log in to the WAPL Admin using valid Super Admin credentials. 2. Navigate to the Dashboard from the sidebar menu. 3. Observe the Active Domains count after the adding the New Domain | Add 1 domain and observe the Active Domain count in Dashboard | The Active Domain box with Count should be visible on the dashboard. | Active Domains Count is Displaying | Pass | High
Verifying Admin Dashboard | TC_WAPL_14 | Verify Certificate Issued Count is Displayed | User must be logged in as Super Admin. | 1. Log in to the WAPL Admin using valid Super Admin credentials. 2. Navigate to the Dashboard from the sidebar menu. 3. Observe the certificate Issued count after issue the certificate for the student | Issue Certificates for Students and observe the Certificate Issued count in Dashboard | The Certificate Issued box with Count should be visible on the dashboard. | Certificate Issued Count is Displaying | Pass | High
Verifying Admin Dashboard | TC_WAPL_15 | Verify Assigned Student Count is Displayed | User must be logged in as Super Admin. | 1. Log in to the WAPL Admin using valid Super Admin credentials. 2. Navigate to the Dashboard from the sidebar menu. 3. Observe the Assigned Student count after assign the student to the HR | Assign the Students to the HR and observe the Assigned Student count in Dashboard | The Assigned Student box with Count should be visible on the dashboard. | Assigned Student Count is Displaying | Pass | High
Verifying Admin Dashboard | TC_WAPL_16 | Verify Student Account Status of Pie Chart | User must be logged in as Super Admin. | 1. Log in to the WAPL Admin using valid Super Admin credentials. 2. Navigate to the Dashboard from the sidebar menu. 3. Observe the Pie Chart Status of Pending ,Active and Suspended Count | Pending the Approval, Active and Suspend the Students and observe the count that was dispalying by the tooltip | The Student Account Status with Tootip Count should be visible on the dashboard. | Student Account Status Count is Displaying | Pass | High
Verifying Admin Dashboard | TC_WAPL_17 | Verify Students per Domain Graph | User must be logged in as Super Admin. | 1. Log in to the WAPL Admin using valid Super Admin credentials. 2. Navigate to the Dashboard from the sidebar menu. 3. Observe the Students per Domai Graph after the Upgrading the students in domain | Add or Delete the students in Domain and observe the Graph count that was dispalying | The Students per Domain and observe the number of students should be visible on the dashboard. | Number of Student Count is Displaying | Pass | High
Verifying Admin Dashboard | TC_WAPL_18 | Verify HR Assignments Graph | User must be logged in as Super Admin. | 1. Log in to the WAPL Admin using valid Super Admin credentials. 2. Navigate to the Dashboard from the sidebar menu. 3. Observe the Graph count after assigning the students to the HR | Assign the Students to the HR and observe the Graph count that was dispalying | The HR Assignments Count and observe the number of students should be visible on the dashboard. | Number of Student Count is Displaying | Pass | High